## Read me
CP-FTMW 310-370 GHz spectrometer - parts list and assembly order
Compiled | 2026-10-07
Basis | chain_purchase_and_design_2026-08-05_rev3.xlsx, sheet 'Final chains (MMD-1030LS)' = plan of record as of 2026-08-05, plus the bench conventions and standing rules from the project record. Nothing here is a new design decision; this workbook reorganises the existing plan into a buildable parts list and a build sequence.
PRICES RE-CHECKED 2026-10-07 - the August decisions have resolved themselves: | See the 'Price check 2026-10-07' sheet for the full table. (1) ZX60-83LN-S+ is now MORE THAN 100 in stock at an unchanged price, so the November interstage bottleneck is GONE and the TB-830A+ bridge is dropped. (2) ZX90-2-24-S+ #2 is 21 in stock, so it is back on the list. (3) The MMD-1030LS priced at $783.20 with ZERO stock and no quotable lead time - the pending 'buy 2x depending on price' decision resolves to NO, and the ZX90 route is now PRIMARY throughout this workbook. (4) ZX60-P105LN+ is the only part still unavailable, with a hard date of 04-Nov-2026 and a 30-week factory lead - so the free interim front-LNA bridges stay for about four more weeks, and the Tx AM-PM gate at step 2.3 is no longer needed.
System band | 310-370 GHz, set by the Tx AMC (ACST 1211B-24AL). The MixAMC's wider ~270-370 GHz good-CL window is dead margin - there is no in-house source below 310 GHz.
Multiplication | AWG 2.152-2.570 GHz -> x3 (ZX90-3-812-S+) -> 6.455-7.710 -> x2 (doubler) -> 12.91-15.42 GHz -> x24 (AMC / MixAMC) -> 310-370 GHz. Total x144 = 43.2 dB phase-noise growth.
Architecture | AWG CH1 = chirp -> Tx chain -> AMC -> horn. AWG CH2 = CW -> an IDENTICAL chain -> MixAMC LO. Both channels share one AWG buffer, which is what gives shot-to-shot phase coherence. Detection window opens only AFTER the chirp ends.
IF | 730-830 MHz (24*f_LO,Rx sits 730 MHz below each segment's low edge). Inside the MixAMC's specified <=1 GHz IF band and clear of the scope's own 1.5 GHz comb.
Which route this list assumes | PRIMARY = the MMD-1030LS route: ONE interstage amp per chain, no 12.5 dB pad, Rx needs no output stage and no second ZX90. FALLBACK (fully specified in the rev3 'Tx chain levels' / 'Rx LO chain levels' sheets) = owned ZX90-2-24-S+ plus TWO interstage stages and a 12.5 dB pad per chain. Parts list marks which rows belong to which route.
What this workbook does NOT cover | PRIMARY (confirmed 2026-10-07 on price and stock) = the ZX90 route: TWO interstage stages per chain with a 12.5 dB pad between them, the owned ZX90-2-24-S+ as the Tx doubler and a second unit for the Rx chain. The MMD-1030LS route is REJECTED on price and availability; its rows are kept and marked so the reasoning stays visible.
Standing rules that shaped the assembly order
1 | Build the Rx LO chain FIRST and clone the settings to Tx. It is CW at every stage, so it is the easier of the two identical chains to debug.
2 | Add ONE element at a time and measure it in place by difference (run_insert.py) against the sweep taken just before it went in. Never characterise a later stage standalone on a synthesiser - different source impedance and, past a multiplier, different input spectrum.
3 | A 10 dB pad lives permanently in front of the scope/EXA. If any pad physically changes, change it in x8_chain/config.py in the same motion. Saved levels stay RAW; the pad is recorded, not applied. Two of the 2026-07-27 scans are unrecoverable because this was not done.
4 | Drive every multiplier at the TOP of its spec window and keep every amplifier >=5 dB below P1dB. The backoff rule is INVERTED for diode multipliers - measured 3.2-3.5 deg/dB AM-to-PM getting WORSE as drive backs off.
5 | Measure flatness at the operating level, never at the AWG ceiling - compression flattens tilt and reported 0.32 dB where the real figure was 0.9.
6 | Measure actual horn-to-horn coupling with a detector BEFORE the MixAMC is ever in the beam, and verify every level on the EXA before connecting either ACST head.

## Price check 2026-10-07
Price and stock re-check, 2026-10-07 (all Mini-Circuits figures from minicircuits.com direct)
Headline | Three things changed and all three point the same way. (1) ZX60-83LN-S+ went from 0/November to MORE THAN 100 in stock, so the interstage bottleneck that forced the whole TB-830A+ bridge is gone. (2) ZX90-2-24-S+ #2 went from 0 to 21 in stock. (3) The MMD-1030LS price finally surfaced at $783.20 with ZERO stock and no quotable lead time. Together these resolve the pending decision AGAINST the MMD route and dissolve most of the November workaround. Only ZX60-P105LN+ is still unavailable, now with a hard date of 04-Nov-2026.
Part | Aug 2026 price | Oct 2026 price | Aug 2026 stock | Oct 2026 stock | Verdict
ZX60-83LN-S+ | 219.09 | 219.09 | 0 - ships ~Nov | more than 100 | CHANGED - buy now. MCL direct only; DigiKey has 0 at $262.91.
ZX90-2-24-S+ | 106.64 | 106.64 | 0 - contact sales | 21 | CHANGED - buy now. Un-cancels the #2 unit for the Rx chain.
ZX90-3-812-S+ | 73.91 | 74.29 | more than 100 | more than 100 | Price +$0.38. The only price movement in the whole list.
ZX60-P105LN+ | 119.47 | 119.47 | 0 - ships ~Nov | 0 - 10 expected 04-Nov-2026 | STILL BLOCKED. 30-week factory lead. The only one left.
VBFZ-2340-S+ | 54.13 | 54.13 | more than 100 | more than 100 | Unchanged.
VBFZ-780-S+ | 54.13 | 54.13 | 55 | 54 | Unchanged.
VHF-4600+ | 33.81 | 33.81 | 230 | 120 | Unchanged price, stock drawing down.
VLF-8400+ | 33.81 | 33.81 | 558 | 197 | Unchanged price, stock drawing down.
BLK-18-S+ | 29.73 | 29.73 | more than 1000 | more than 1000 | Unchanged.
141-12SM+ | 17.13 | 17.13 | more than 1000 | more than 1000 | Unchanged.
K5-BW1+ | 378.24 | 378.24 | 2 (!) | 7 | Unchanged price, pressure eased. DigiKey 0.
ZRL-3500+ (contingency) | 185.88 | 185.88 | 47 | 94 | Unchanged. Only needed if the H242 edge check fails.
Marki MMD-1030LS |  | 783.2 | price unknown | 0 in stock, 0 factory stock | REJECTED - see below. $737.13 at qty 5-9.
TB-830A+ (interim) | 141.61 |  | MMIC >1000 | not needed | DROPPED - the real ZX60-83LN-S+ is in stock.
The MMD-1030LS decision, resolved
MMD route, both chains
ZX90 route, both chains
ZX90 route saves |  | ...and is the only one of the two that can actually be delivered.
What the MMD would still have bought, for the record
- | Two fewer boxes per chain (one interstage amp instead of two, no 12.5 dB pad).
- | F1 rejection 38 dBc vs the owned ZX90's 21.9 dBc dip at 7.0 GHz - but that dip is out of band, and ACST say out-of-band content does not matter to the AMC.
- | An Rx output landing on -6.0 dBm with zero trim parts, instead of +0.3 dBm into a 6 dB pad.
- | Against all that: it would have been driven at +6.8 dBm, 8 dB below its window top, straight into the backed-off regime your own AM-PM bench work identified as the bad one for a diode multiplier. Rejecting it also removes that gate from the build.
BASKET TO ORDER NOW - all in stock at Mini-Circuits direct
Part | Unit USD | Qty | Ext USD |  | Note
ZX60-83LN-S+ | 219.09 | 4 |  |  | Interstage, 2 per chain. The big change - in stock now.
ZX90-3-812-S+ | 74.29 | 2 |  |  | Tripler, 1 per chain.
VBFZ-2340-S+ | 54.13 | 2 |  |  | Front BPF, 1 per chain.
VHF-4600+ | 33.81 | 2 |  |  | Post-tripler HPF, 1 per chain.
VLF-8400+ | 33.81 | 2 |  |  | Post-tripler LPF, 1 per chain.
ZX90-2-24-S+ | 106.64 | 1 |  |  | Rx doubler #2. Tx uses the owned unit.
VBFZ-780-S+ | 54.13 | 1 |  |  | IF bandpass.
BLK-18-S+ | 29.73 | 1 |  |  | IF DC block.
K5-BW1+ | 378.24 | 1 |  |  | Pad kit - every 3 / 6 / 12.5 dB trim.
141-12SM+ | 17.13 | 8 |  |  | Hand-Flex SMA interconnect.
Subtotal, order now
ZX60-P105LN+ | 119.47 | 3 |  |  | DEFERRED to ~04-Nov-2026. 2 front LNAs + 1 IF amp. Place the order now so you are in the queue; bridge with owned parts until it lands.
TOTAL
Versus August | Essentially the same money - the 2026-08-05 basket came to $2,331.87 - but with $0 of interim spend instead of $283-566 of TB-830A+ boards, no open-PCB bench-supply wiring, no $1,566 of Marki doublers, and everything except the three P105LNs shipping today.
Sources | minicircuits.com WebStore dashboards per model (prices and stock, fetched 2026-10-07); shop.markimicrowave.com and rfmw.com product detail 710279 for the MMD-1030LS, which agree on $783.20 / 0 stock; digikey.com for the ZX60-P105LN+ 04-Nov-2026 date and the ZX60-83LN-S+ distributor comparison. mouser.de timed out on automated fetch, as it has before - check it by hand if you want EU-side pricing.

## Parts list
Section | # | Slot / function | Part | Qty | Have / buy | Unit USD (MCL list 2026-08-05) | Route | Notes
A - Instruments and control (all owned, already working)
A | 1 | Arbitrary waveform generator | Tabor Proteus P9482D | 1 | OWNED |  | both | LAN 141.51.196.111:5025. AC-coupled direct-DAC output module: 9 GHz BW, 550 mVpp ceiling - keep every DUC amplitude <=0.5 Vpp or :VOLT is silently rejected. DUC order that works on fw 1.237.0: :MODE DUC -> :SOUR:INT X8 -> :FREQ:RAST 9e9 -> :SOUR:IQM ONE LAST, then readback-verify == ONE.
A | 2 | FID / IF digitiser | Tektronix MSO64B | 1 | OWNED |  | IF | TCPIP::169.254.4.20::4000::SOCKET (raw socket - USB had a 30 s SCPI-blocking bug). 50 ohm input, max 5 V RMS. Needs a common 10 MHz ref with the AWG for coherent averaging.
A | 3 | Signal analyser - every level and spur check | Keysight N9010A EXA | 1 | OWNED |  | both | USB0::0x0957::0x0B0B::MY52220585::INSTR. Max RBW is 3.000 MHz and a wider request is SILENTLY clamped - always read back get_rbw(). For a pulsed or swept signal use MAXH + clear_trace(), never a Normal single sweep (47.8 dB vs 0.6 dB spread across a flat band).
A | 4 | Interim Rx LO for first light | R&S SMB100A | 1 | OWNED |  | Rx LO | Firmware-enforced +13 dBm ceiling. Drives the MixAMC LO at -6 dBm for first light, locked to the shared 10 MHz. NOT usable for coherent averaging - its phase is not shot-repeatable.
B - Tx chain: AWG CH1 -> AMC (weak-edge design levels from rev3 'Final chains')
B | 1 | AWG CH1 out, 0.55 Vpp -> -5.5 dBm | 141-12SM+ Hand-Flex 12 in SMA | 1 | BUY - IN STOCK |  | both | [2026-10-07] Price unchanged, stock >1000. No pad between the AWG and the first amp - a pad there costs C/N dB for dB. -0.5 dB cable. Priced under F2, not separately - these four slot cables come out of the 8-cable allowance.
B | 2 | Front LNA -> +9.5 dBm | ZX60-P105LN+ | 1 | BUY - ~4 WKS | 119.47 | both | [2026-10-07 PRICE CHECK] THE ONLY REMAINING OUT-OF-STOCK PART. MCL direct still 0 ('contact Sales'); DigiKey gives the hard date: 0 in stock, 10 expected 04-Nov-2026, 30-week factory lead, $143.36 at qty 1 (so still buy from MCL at $119.47). The November story was real but it now applies to THIS SLOT ONLY - front LNAs and the IF amp - not to the interstage. Keep the free interim bridges for ~4 weeks. NF ~0.9, G 15.5, P1dB +18.9 = 9.4 dB backoff. INTERIM: owned ZX60-H242+ (free) but its spec ENDS at 2.4 GHz and the band tops at 2.57 - GATE with a 10-minute EXA gain-tilt check first. Contingency if that fails: ZRL-3500+, $185.88, NF 2.3, G 22, P1dB +24.
B | 3 | Noise-free level trim -> +6.5 dBm | 3 dB pad (from K5-BW1+ kit) | 1 | BUY - IN STOCK |  | both | [2026-10-07] Price unchanged at $378.24 and stock eased 2 -> 7. Still order it early; DigiKey has 0. Pads AFTER the first amp are free - the signal is >100 dB above kT.
B | 4 | BPF 2020-2660 MHz -> +4.5 dBm | VBFZ-2340-S+ | 1 | BUY - IN STOCK | 54.13 | both | [2026-10-07] Price unchanged, stock >100. Kills LNA harmonics and AWG DAC/DUC images before the tripler. -2 dB with interconnect.
B | 5 | Tripler x3 -> -10.5 dBm | ZX90-3-812-S+ | 1 | BUY - IN STOCK | 74.29 | both | [2026-10-07 PRICE CHECK] The only price that moved since August: $73.91 -> $74.29 (+$0.38). Stock still >100. In 2.0-2.7, out 6.0-8.1 GHz, drive window 0..+5 dBm - drive at the TOP (+4.5). CL 15 typ / 22 max. F1 only 30 typ / 21 min dBc, which is what makes the next filter load-bearing.
B | 6 | HPF -> -11.7 dBm | VHF-4600+ | 1 | BUY - IN STOCK | 33.81 | both | [2026-10-07] Price unchanged, stock 120 (was 230). Pass 5.2-10.5 GHz. Kills the tripler's 2.15-2.57 GHz F1 leak-through. LOAD-BEARING.
B | 7 | LPF -> -13.0 dBm | VLF-8400+ | 1 | BUY - IN STOCK | 33.81 | both | [2026-10-07] Price unchanged, stock 197 (was 558). Kills F4+ and the F2 residue at 4.30-5.14 GHz, which would otherwise land IN BAND at 12.9-15.4 GHz after the doubler. NOT VHF-8400+ - that part's passband ends at 13 GHz and cannot pass 15.42.
B | 8 | Interstage amp -> +6.8 dBm | ZX60-83LN-S+ | 1 | DO NOT BUY | 219.09 | REJECTED (MMD) | [2026-10-07 PRICE CHECK] REJECTED with the MMD-1030LS - see that row. G 19.8, 12.7 dB below P1dB. SINGLE stage on this route, no 12.5 dB pad. INTERIM: TB-830A+ ($141.61) - eval board of PMA3-83LN+, the same MMIC inside the ZX60; MMIC stock >1000, the puck assembly is the Nov bottleneck. Open PCB, needs +5 V bench supply; CONFIRM it ships with SMA.
B | 8 | ALTERNATIVE interstage: two stages + pad -> +12.3 dBm | ZX60-83LN-S+ x2 + 12.5 dB pad | 2 | BUY - IN STOCK | 219.09 | PRIMARY | [2026-10-07 PRICE CHECK] NOW THE PRIMARY ROUTE. MCL direct stock flipped 0 -> MORE THAN 100 at an unchanged $219.09, so the November bottleneck on this part is GONE and the TB-830A+ bridge is no longer needed. Buy from MCL DIRECT, not a distributor: DigiKey shows 0 in stock, 10 expected 27-Oct-2026, at $262.91 - i.e. $43.82/unit more for a part MCL has on the shelf. Only if the MMD-1030LS is not bought. 19 dB -> 12.5 dB pad -> 18.8 dB lands +12.3 dBm, which is what the owned ZX90-2-24-S+ needs (its floor is +11, so 1.3 dB of margin). Second stage sits at 5.7 dB backoff - right at the >=5 dB rule edge.
B | 9 | Doubler x2 -> -5.7 dBm, out 12.91-15.42 GHz | Marki MMD-1030LS | 1 | DO NOT BUY | 783.2 | REJECTED | [2026-10-07 PRICE CHECK] DECISION RESOLVED - NO. $783.20 at qty 1-4 ($737.13 at 5-9), and 0 in stock AND 0 factory stock with no quotable lead time (Marki shop and the RFMW mirror agree). Two units = $1,566.40 against $983.00 for the ZX90 route whose parts are all on the shelf today - $1,021.58 more for a part that cannot be delivered. Your standing decision was 'buy 2x depending on price'; the price answers it. The AM-PM gate at step 2.3 also disappears with it, since +6.8 dBm would have sat 8 dB below this part's window top. In 5-15, out 10-30 GHz, drive 5-15 nom +7, CL 12.5/14, F1 38 dBc, F3 46 dBc. SMA in / 2.92 out. +6.8 dBm drive is 8 dB below window top -> GATE with run_am_pm.py A/B against the owned ZX90 before committing it to the CHIRP path. Marki shop / RFMW are bot-blocked - price manually.
B | 9 | ALTERNATIVE doubler -> +0.3 dBm | ZX90-2-24-S+ (#1) | 1 | OWNED |  | PRIMARY | [2026-10-07 PRICE CHECK] Now the primary Tx doubler - the MMD-1030LS is rejected. CL measured 11.7-12.9 dB on this bench. Its 21.9 dBc F1 dip at 7.0 GHz is out of band and ACST say out-of-band content does not matter to the AMC. Needs the two-stage interstage above.
B | 10 | Trim pad (ZX90 route only) | 3 dB pad (from kit) | 1 | BUY (kit) |  | PRIMARY | Set on the bench to land the AMC at ~+5 dBm. Not needed on the MMD route.
B | 11 | Output amp -> +5.3 dBm | ZX60-04183LN+ | 1 | OWNED |  | both | 4-18 GHz, G ~11 at 14 GHz, P1dB +15 = ~13 dB backoff. The only on-hand amp covering 13-15 GHz.
B | 12 | Isolator -> +4.4 dBm | PE83IR1023 | 1 | OWNED |  | both | 8-18 GHz, IL 1.4 dB max, 32 dB isolation. Protects the doubler and amp from AMC input reflections.
B | 13 | Cable to AMC -> +3.8 dBm at the AMC input | 141-12SM+ Hand-Flex | 1 | BUY - IN STOCK |  | both | [2026-10-07] Price unchanged, stock >1000. AMC window is 0..+7 dBm, typ +5. Weak edge lands +3.8, strong edge +5.1 - in window, near typ. No output filter (ACST: out-of-band content does not matter). If the bench wants more, revert to the ZX90 route or add a second amp. Priced under F2, not separately - these four slot cables come out of the 8-cable allowance.
C - Rx LO chain: AWG CH2 -> MixAMC LO (identical to B through the doubler, second units)
C | 1 | AWG CH2 out, CW -> -5.5 dBm | 141-12SM+ Hand-Flex 12 in SMA | 1 | BUY - IN STOCK |  | both | [2026-10-07] Price unchanged, stock >1000. Per-segment CH2 amplitude scalars are LOAD-BEARING: they hold -6.0 dBm at the MixAMC across the 1.3 dB band tilt AND keep the conversion loss drive-constant from segment to segment. Priced under F2, not separately - these four slot cables come out of the 8-cable allowance.
C | 2 | Front LNA -> +9.5 dBm | ZX60-P105LN+ | 1 | BUY - ~4 WKS | 119.47 | both | [2026-10-07 PRICE CHECK] THE ONLY REMAINING OUT-OF-STOCK PART. MCL direct still 0 ('contact Sales'); DigiKey gives the hard date: 0 in stock, 10 expected 04-Nov-2026, 30-week factory lead, $143.36 at qty 1 (so still buy from MCL at $119.47). The November story was real but it now applies to THIS SLOT ONLY - front LNAs and the IF amp - not to the interstage. Keep the free interim bridges for ~4 weeks. INTERIM: owned ZX60-123LN-S+ (free, in spec 0.5-12 GHz, NF 2.1 = best on hand, G 18.9, P1dB +16.5). Only 2-4 dB of backoff, which is acceptable HERE because the LO is CW - no envelope, so no AM-PM. For exactly that reason it is NOT usable in the Tx front slot.
C | 3 | Level trim -> +6.5 dBm | 3 dB pad (from kit) | 1 | BUY (kit) |  | both | Same as B3.
C | 4 | BPF 2020-2660 MHz -> +4.5 dBm | VBFZ-2340-S+ | 1 | BUY - IN STOCK | 54.13 | both | [2026-10-07] Price unchanged, stock >100. Second unit.
C | 5 | Tripler x3 -> -10.5 dBm | ZX90-3-812-S+ | 1 | BUY - IN STOCK | 74.29 | both | [2026-10-07 PRICE CHECK] The only price that moved since August: $73.91 -> $74.29 (+$0.38). Stock still >100. Second unit.
C | 6 | HPF -> -11.7 dBm | VHF-4600+ | 1 | BUY - IN STOCK | 33.81 | both | [2026-10-07] Price unchanged, stock 120 (was 230). Second unit.
C | 7 | LPF -> -13.0 dBm | VLF-8400+ | 1 | BUY - IN STOCK | 33.81 | both | [2026-10-07] Price unchanged, stock 197 (was 558). Second unit.
C | 8 | Interstage amp -> +6.8 dBm | ZX60-83LN-S+ | 1 | DO NOT BUY | 219.09 | REJECTED (MMD) | [2026-10-07 PRICE CHECK] REJECTED with the MMD-1030LS - see that row. Single stage, as B8. INTERIM: TB-830A+. On the ZX90 fallback this becomes 2 units + a 12.5 dB pad.
C | 9 | Doubler x2 -> -5.7 dBm | Marki MMD-1030LS | 1 | DO NOT BUY | 783.2 | REJECTED | [2026-10-07 PRICE CHECK] DECISION RESOLVED - NO. $783.20 at qty 1-4 ($737.13 at 5-9), and 0 in stock AND 0 factory stock with no quotable lead time (Marki shop and the RFMW mirror agree). Two units = $1,566.40 against $983.00 for the ZX90 route whose parts are all on the shelf today - $1,021.58 more for a part that cannot be delivered. Your standing decision was 'buy 2x depending on price'; the price answers it. The AM-PM gate at step 2.3 also disappears with it, since +6.8 dBm would have sat 8 dB below this part's window top. Output lands AT the MixAMC's -6 dBm target with zero further parts - this is the single biggest argument for the part. CW here, so nominal drive is fine and no AM-PM gate is needed on this unit.
C | 9 | ALTERNATIVE doubler -> +0.3 dBm, then a 6 dB pad | ZX90-2-24-S+ (#2) | 1 | BUY - IN STOCK | 106.64 | PRIMARY | [2026-10-07 PRICE CHECK] UN-CANCELLED and now buyable: MCL direct stock flipped 0 -> 21 at an unchanged $106.64. The owned MMD-0415HS off-spec bridge is no longer needed. CANCELLED on the MMD route. Note KSX2-24+ ($6.88, stock >1000) is the same die, with a TB-KSX2-24+ board, if the connectorised puck is the holdup. INTERIM bridge: owned MMD-0415HS, off-spec at both band tops (7.71 vs 7.5 in, 15.42 vs 15 out) but CW-tolerable.
C | 10 | Final trim -> -6.0 dBm at the MixAMC LO port | 0-1 dB pad + cable | 1 | BUY (kit) |  | both | HARD GATE: the MixAMC LO window is -8 min / -6 typ / -2 MAX dBm. Verify on the EXA before the first connect and NEVER exceed -2. No output amp and no isolator on this chain - a 6 dB pad already gives 12 dB of return isolation for a CW LO.
D - IF chain: MixAMC IF -> scope
D | 1 | DC block at the IF port | BLK-18-S+ | 1 | BUY - IN STOCK | 29.73 | both | [2026-10-07] Price unchanged, stock >1000. -0.2 dB. Stays in until ACST confirm there is no DC on the IF port.
D | 2 | IF bandpass 710-850 MHz | VBFZ-780-S+ | 1 | BUY - IN STOCK | 54.13 | both | [2026-10-07] Price unchanged, stock 54. -1.8 dB. BEFORE the LNA, deliberately: the chirp's detected-envelope/video transient (DC to a few MHz) dies 60-80 dB before any amplification, and the insertion loss costs only ~0.03 dB of NF behind the MixAMC's internal +20 dB. Stopband >=30 dB below 440 MHz and across 1.32-16 GHz, which kills both the CH2 leak at 2.15-2.57 GHz and the internal x12 chain leak at 12.9-15.4 GHz. Bandpass, not lowpass, so low-frequency junk dies too (user's call 2026-08-05).
D | 3 | IF LNA | ZX60-P105LN+ | 1 | BUY - ~4 WKS | 119.47 | both | [2026-10-07 PRICE CHECK] THE ONLY REMAINING OUT-OF-STOCK PART. MCL direct still 0 ('contact Sales'); DigiKey gives the hard date: 0 in stock, 10 expected 04-Nov-2026, 30-week factory lead, $143.36 at qty 1 (so still buy from MCL at $119.47). The November story was real but it now applies to THIS SLOT ONLY - front LNAs and the IF amp - not to the interstage. Keep the free interim bridges for ~4 weeks. NF ~0.9, G 15.5. ONE external stage - the internal +20 dB does most of the work. INTERIM: run AMPLESS (~1.8 dB NF penalty, fine for first light), or the freed H242 if a ZRL-3500+ was bought for the Tx front. ZFL-1000LN+ is REJECTED - its P1dB +3 would clip the chirp leak by ~10 dB.
D | 4 | Cable to scope, 50 ohm | 141-12SM+ Hand-Flex | 1 | BUY - IN STOCK |  | both | [2026-10-07] Price unchanged, stock >1000. Leak at the scope is 0.60 V RMS at Tx typ, 1.34 V RMS at AMC max - safe against the 50 ohm input's 5 V RMS limit. Priced under F2, not separately - these four slot cables come out of the 8-cable allowance.
E - mm-wave front end (ACST quote A-241209-2, already quoted/ordered)
E | 1 | Tx x24 AMC, out 310-370 GHz | ACST 1211B-24AL | 1 | ACST |  | both | In 12.91-15.42 GHz (SMA), out WR-2.8. Input 0 / +5 typ / +7 max dBm - a window only 7 dB wide, and the binding constraint on the whole Tx chain. Output +8 min / +10 typ / +17 max dBm. An optional integrated 1-25 dB variable attenuator exists for level control.
E | 2 | Rx subharmonic mixer + x12 AMC = x24 | ACST MixAMC WR2.8, 250-400 GHz | 1 | ACST |  | both | LO -8 min / -6 typ / -2 MAX dBm - only a 6 dB window. Internal IF gain +20 dB; CL 6/8/30 dB, usable window ~270-370 GHz; IF spec'd <=1 GHz. Net RF->IF gain +12 dB typ. RF port is linear below -10 dBm and DAMAGED at 0 dBm.
E | 3 | Horn antennas, ~25 dBi class | ACST 527G WR-2.8 horn | 2 | ACST |  | both | One on the AMC, one on the MixAMC, facing at >=0.5 m. That geometry gives about -27 dB of coupling (Friis), so the chirp leak is -17 dBm at Tx typ: inside the mixer's linear range with ~7 dB of margin. Do NOT add quasi-optical focusing - it would couple far more and destroy the mixer.
F - Shared, test and infrastructure
F | 1 | All trim pads (3 / 6 / 12.5 dB slots) | K5-BW1+ SMA attenuator kit | 1 | BUY - IN STOCK | 378.24 | both | [2026-10-07] Price unchanged at $378.24 and stock eased 2 -> 7. Still order it early; DigiKey has 0. ORDER EARLY - only 2 kits were in stock at MCL direct on 2026-08-05. Verify the kit values cover 3, 6 and 12.5 dB before relying on it.
F | 2 | Interconnect throughout | 141-12SM+ Hand-Flex 12 in SMA | 8 | BUY - IN STOCK | 17.13 | both | [2026-10-07] Price unchanged, stock >1000. Eight is the rev3 allowance; the per-slot cable rows above are drawn from this quantity.
F | 3 | Thru reference for every insertion measurement | SMA barrel / union, DC-18 GHz | 2 | BUY |  | both | run_stage_gain.py measures a 'thru' with the amp replaced by a barrel, then the amp, and takes the difference point by point so every pad, cable and calibration error cancels exactly.
F | 4 | Permanent instrument-input pad | 10 dB pad, DC-18 GHz | 1 | OWNED |  | both | The campaign convention: it never moves, so it is a constant of the setup rather than a per-run variable. Recorded in x8_chain/config.py and written into every saved file's metadata.
F | 5 | Shared 10 MHz reference | BNC cable, scope REF OUT -> AWG REF IN | 1 | MISSING - BUY |  | both | BLOCKS COHERENT AVERAGING. AWG.set_reference_external(10) is already written and called. Without a shared reference the two timebases drift differently every shot, which align_and_average() cannot undo - it only corrects a constant offset, and the error worsens with chirp frequency. Unverified whether this scope's REF OUT is always on or needs enabling.
F | 6 | Bias for the interim eval boards | +5 V bench supply + wiring | 1 | NOT NEEDED |  | interim only | [2026-10-07 PRICE CHECK] NO LONGER NEEDED - the TB-830A+ open-PCB bridge is dropped now that the connectorised ZX60-83LN-S+ is in stock. TB-830A+ ships as an open PCB with a DC pin - 2 or 4 boards depending on route. Not needed once the connectorised ZX60-83LN-S+ pucks arrive.
F | 7 | Scope trigger from the AWG marker | Marker cable - CONNECTOR UNRESOLVED | 1 | BLOCKED |  | both | Tabor's documentation says SMP but the physical connector is threaded with a protruding centre pin, so it is probably SMC or 1.0/2.3. Identify it before ordering. A marker trigger fixes the trigger problem at the root (clean digital edge, no RF cycle ambiguity) and frees CH2 from the scope, unlocking a faster sample-rate tier. Granularity at 9 GS/s is 8 samples = 0.89 ns, with :MARKer:DELay:FINE giving +/-0.6 ns of trim.
|  | Line-item total of every priced row above - includes the REJECTED MMD-1030LS rows and both interstage variants, so it is NOT a basket to order. The basket to order is on the 'Price check 2026-10-07' sheet. |  |  | TOTAL USD
Reference subtotals from rev3, 2026-08-05 MCL list prices: permanent passives ~$990 (order now regardless of route) ¦ interim TB-830A+ bridge $283 for 2 boards on the MMD route, $566 for 4 on the ZX90 route ¦ ZRL-3500+ contingency $186 ¦ 2x MMD-1030LS price TBD ¦ full November amp order 3x ZX60-P105LN+ and 2-4x ZX60-83LN-S+.

## Assembly order
Phase | Step | Action | Measure with | Pass criterion / gate
PHASE 0 - bench infrastructure, before any RF is connected
0 | 0.1 | Bring up the three instruments and confirm comms: AWG over LAN, scope over raw socket, EXA over USB. | awg.py / scope.py / specan.py | *IDN? on all three. EXA connect drains stale replies and calls inst.clear() first.
0 | 0.2 | Fit the permanent 10 dB pad at the EXA/scope input and record it, plus every other pad, in x8_chain/config.py. | x8_chain/config.py | config.py matches the physical bench exactly. Every script imports it and writes it into each saved file's metadata.
0 | 0.3 | Fit the 10 MHz reference cable, scope REF OUT -> AWG REF IN, and enable the external reference. | AWG.set_reference_external(10) | Cable is MISSING - buy it. Confirm whether the scope's REF OUT is always on or needs its own command. Not a blocker for single-shot level work; it IS a blocker for coherent averaging.
0 | 0.4 | Verify the AWG's DUC operating point and CH1/CH2 output levels at the band edges. | EXA, MAXH; run_awg_level_scope.py | :SOUR:IQM? must read ONE. Expect about -5.5 dBm at the weak edge 2.570 GHz and -4.24 at the strong edge, i.e. 1.27 dB of tilt, at the 0.55 Vpp ceiling.
PHASE 1 - Rx LO chain, element by element (CW, no mm-wave part in the room yet)
1 | 1.1 | AWG CH2 -> cable -> front LNA. Thru first with a barrel, then the amp. | run_drive_level.py then run_stage_gain.py thru / amp | GATE if using the interim: ZX60-123LN-S+ is in spec, so this one is clean. Expect ~+9.5 dBm out. Sweep a ladder of output levels, not just the operating point - warn if mean gain falls >0.3 dB on the upper rungs.
1 | 1.2 | Add the 3 dB pad and the VBFZ-2340-S+ bandpass. | run_insert.py | Insertion loss and tilt by difference against step 1.1. Budget is -2 dB including interconnect, landing +4.5 dBm.
1 | 1.3 | Add the ZX90-3-812-S+ tripler, driven at +4.5 dBm. | run_insert.py difference sweep at 0 and +5 dBm drive | Conversion loss at our exact band (budget 15 dB typ, 22 max) and F1 / F2 / F4 rejection. F1 is spec'd at only 30 typ / 21 min dBc - this measurement sizes how hard the next filter must work.
1 | 1.4 | Add the VHF-4600+ high-pass, then the VLF-8400+ low-pass, one at a time. | run_insert.py | F1 at 2.15-2.57 GHz suppressed by the HPF; F2 residue at 4.30-5.14 GHz suppressed by the LPF - that residue is the one that would land IN BAND at 12.9-15.4 GHz after the doubler. Level -13.0 dBm.
1 | 1.5 | Add the interstage amplifier. MMD route: one stage to +6.8 dBm. ZX90 route: two stages with a 12.5 dB pad between, to +12.3 dBm. | run_stage_gain.py thru / amp | Backoff >=5 dB from P1dB. On the ZX90 route the second stage sits at 5.7 dB - right at the rule edge, so verify rather than assume.
1 | 1.6 | Add the doubler. Output is 12.91-15.42 GHz. | run_insert.py CL and spur sweep at the real drive level | MMD-1030LS: CL 12.5/14 at +6.8 dBm drive, F1 38 dBc, F3 46 dBc, out -5.7 dBm. ZX90-2-24-S+: CL 11.7-12.9 measured on this bench, drive +12.3 against its +11 floor, out +0.3 dBm. No AM-PM gate needed on this chain - it is CW.
1 | 1.7 | Trim the final pad to land exactly -6.0 dBm, measured at the plane where the MixAMC LO port will connect. | EXA | HARD GATE. Window is -8 / -6 typ / -2 MAX dBm. Never exceed -2. Do this BEFORE the MixAMC is ever cabled.
1 | 1.8 | Build the per-segment CH2 amplitude scalar table. | x8_chain/run_segments.py | One scalar per segment, not a fine correction table - within a segment the residual is pure tilt. Target: hold -6.0 dBm across the 1.3 dB band tilt and keep the MixAMC's conversion loss drive-constant from segment to segment. AWG-alone precedent: 1.28 -> 0.025 dB.
PHASE 2 - Tx chain: clone Phase 1 with the second set of parts, then add the output stage
2 | 2.1 | Repeat 1.1-1.4 with the Tx units and the Tx front amp. | run_stage_gain.py / run_insert.py | GATE if bridging with the owned ZX60-H242+: its spec ENDS at 2.4 GHz and the band tops at 2.57 - run the 10-minute EXA gain-tilt check across 2.4-2.57 GHz first. If it fails, buy the ZRL-3500+.
2 | 2.2 | Repeat 1.5-1.6 with the Tx interstage amp and the Tx doubler. | run_insert.py | Same criteria as 1.5-1.6. Reuse the Rx chain's settings as the starting point - that is the whole reason the Rx chain is built first.
2 | 2.3 | AM-to-PM ladder on the Tx doubler, A/B against the owned ZX90-2-24-S+. | x8_chain/run_am_pm.py | THE GATE that decides whether the MMD-1030LS may carry the CHIRP. At +6.8 dBm it sits 8 dB below its window top, and the measured rule on this bench is that a diode multiplier gets WORSE backed off: 3.2-3.5 deg/dB at the operating point, rising to r = 2.52 at -6 dB. Fallback is the owned ZX90 plus two interstage stages.
2 | 2.4 | Add the 3 dB trim pad (ZX90 route), the ZX60-04183LN+ output amp and the PE83IR1023 isolator. | run_insert.py | Amp at ~13 dB backoff. Isolator IL 1.4 dB max.
2 | 2.5 | Measure the level at the AMC input plane across the whole band. | EXA, MAXH | HARD GATE before the AMC is ever cabled. Must sit inside 0..+7 dBm with the target near +5. Design value is +3.8 weak edge / +5.1 strong edge. If it is short, revert to the ZX90 route or add a second amp - do not connect and hope.
2 | 2.6 | Measure the tilt transfer ratio through the doubler, and the segment-to-segment spread at the AMC plane. | run_insert.py, run_segments.py | A square-law doubler doubles small-signal dB tilt; hard saturation drives it toward zero. The design assumes compression helps. Measure Pout vs Pin - this assumption currently rests on unmeasured parts.
2 | 2.7 | Apply chirp pre-emphasis and per-segment CH1 scalars. | x8_chain/run_preemph.py, run_segments.py | Go straight to digital baseband scaling on the chirp envelope - :VOLT quantisation floors out at 0.0046 dB rms and cannot reach the -36 dBc paired-echo target, while 15-bit digital scaling reaches the measurement floor. Pre-emphasis is phase-safe: 2.4 dB of correction at 0.037 deg/dB is 17 deg after x144.
PHASE 3 - mm-wave front end. The order here is a safety rule, not a convenience.
3 | 3.1 | Mount the AMC and one 527G horn. Mount the second horn facing it at >=0.5 m. Do not install the MixAMC yet. | mechanical | Needs a rail / mount and alignment hardware that is NOT in the project record - see Gaps. Plain facing horns only. NO quasi-optical focusing.
3 | 3.2 | With Tx running, measure the actual power arriving at the receive horn using a detector or power meter in the MixAMC's place. | mm-wave detector / power meter - see Gaps | STANDING RULE, HARD GATE: this happens before the mixer is ever in the beam. Expect about -27 dB of coupling, i.e. -17 dBm at Tx typ. The MixAMC RF port is linear below -10 dBm and DAMAGED at 0. If the measured coupling is tighter than about -17 dB, increase the separation or use the AMC's optional 1-25 dB attenuator before proceeding.
3 | 3.3 | Only after 3.2 passes: install the MixAMC behind the receive horn. | - | There is no SPDT switch available anywhere in 310-370 GHz at any price - protection comes from the power budget and the geometry, and gating comes from the AWG (passive chain, so AWG off = no 340 GHz output). Switch the IF, never the RF.
PHASE 4 - IF chain
4 | 4.1 | MixAMC IF (K connector) -> BLK-18-S+ DC block. | - | Stays in until ACST confirm there is no DC on the IF port. Optional 3 dB pad here if the IF port wants a broadband match.
4 | 4.2 | Add the VBFZ-780-S+ bandpass BEFORE any amplifier. | EXA / scope | Order matters: the chirp's video transient dies 60-80 dB before amplification. Passband 710-850 MHz against an IF band of 730-830, i.e. 20 MHz of margin each side.
4 | 4.3 | Add the external IF LNA, or run ampless for first light. | scope, 50 ohm | Ampless costs ~1.8 dB of NF and works - the internal +20 dB carries it. With the LNA, leak at the scope is 0.60 V RMS at Tx typ against a 5 V RMS limit.
PHASE 5 - first light, with the SMB100A standing in as the Rx LO
5 | 5.1 | Drive the MixAMC LO from the SMB100A at -6 dBm, locked to the shared 10 MHz. Tx CW, not chirped. | scope / EXA | An IF tone appears, even ampless. This buys the end-to-end check with zero new parts and does not wait on the November amps.
5 | 5.2 | Map conversion loss and real horn coupling across 310-370 GHz. | scope / EXA | Plan around ~8 dB CL. Watch the 370 GHz edge - the 30 dB max figure is the below-270 corner, but the top edge is unmeasured on this unit.
5 | 5.3 | Do NOT attempt coherent averaging on this configuration. | - | The synth's phase is not shot-repeatable. Also: this synth measured ~9 dB worse close-in spurs at 12.42 GHz than at 10.42/11.42, consistent with an internal divider-band boundary.
PHASE 6 - swap in the CH2 chain and close coherence
6 | 6.1 | Replace the SMB100A with the Phase 1 CH2 chain at -6 dBm. | EXA before connecting | Re-verify the level at the LO plane after the swap. Never above -2 dBm.
6 | 6.2 | Set the frequency plan: 24*f_LO,Rx exactly 730 MHz below each segment's low edge, CH2 stepping in lockstep with CH1's NCO. | awg.py DUC NCO stepping | f_CH2 = (f_seg,low - 0.730)/144. For 100 MHz segments CH2 sits 5.417 MHz below the CH1 segment-centre equivalent. LO always BELOW the segment, which keeps it <=369.3 GHz and inside the MixAMC's good-CL window, and maps the segment to one non-inverted sideband.
6 | 6.3 | Trigger the scope on the AWG marker rather than on RF, and confirm both instruments are on the shared 10 MHz. | marker cable - connector unresolved | Both are prerequisites for coherent averaging: x144 multiplies phase error by 43.2 dB, so deterministic ripple calibrates out but random cross-instrument drift does not. Keep align_and_average() as a robustness check even after the marker trigger works.
6 | 6.4 | Open the detection window only AFTER the chirp ends, and record FID x LO. | scope | By construction the chirp-leak beat never enters recorded data. It matters only for mixer safety during the chirp and for how fast the IF chain and scope settle before the window opens - and that settling time now hinges on the MixAMC's INTERNAL IF amp recovery, which is still an open question to ACST.
PHASE 7 - sample region. Not designed. See the Gaps sheet.
7 | 7.1 | Everything above produces and detects 310-370 GHz across a free-space path. It does not yet constitute a spectrometer: there is no sample. | - | A chamber, pumping, gas handling and a pulsed source (or a static absorption path) have to be designed and their geometry reconciled with the >=0.5 m horn separation and the Phase 3 coupling gate. This is the one subsystem with nothing in the project record.

## Gaps + open items
Kind | Item | Why it matters | Status / what to do
GAP - subsystem | Sample region: vacuum chamber, pumping, gas handling, pulsed nozzle or static absorption path | The entire project record covers the RF/mm-wave chain and the instruments. The only thing between the horns is ~0.5 m of free space. Without a sample there is no spectrometer. | NOT DESIGNED. Needs its own pass. Its geometry has to be reconciled with the >=0.5 m horn separation and the Phase 3 coupling gate - windows or a chamber in the beam path change the coupling that gate measures.
GAP - hardware | mm-wave detector or power meter for 310-370 GHz | Phase 3.2 is a standing safety rule: measure the power at the receive-horn position BEFORE the MixAMC is ever in the beam. The mixer is damaged at 0 dBm. | No such instrument appears anywhere in the project record. Confirm whether one is on hand or borrowable; the Phase 3 gate cannot be run without it, and skipping it risks the 24.35k EUR MixAMC.
GAP - hardware | Horn mounts, rail and alignment hardware; WR-2.8 flange hardware | Two horns have to face each other at a known, repeatable >=0.5 m separation. Coupling goes as the square of distance and alignment is unforgiving at 0.8 mm wavelength. | Not in the record. Specify alongside the sample region, since they share the same optical bench.
MISSING PART | BNC cable, scope REF OUT -> AWG REF IN | Blocks coherent averaging. Software alignment corrects only a constant per-shot offset, not two timebases drifting at independent ppm rates, and the error grows with chirp frequency. | Buy. Also determine whether this scope's REF OUT is always active or needs its own command - there is no local manual for this model.
BLOCKED | AWG marker-output cable | A marker trigger fixes the scope trigger at the root - clean digital edge, no RF cycle ambiguity, no carrier-frequency confound - and frees CH2 from the scope, unlocking a faster sample-rate tier. | Connector type UNRESOLVED: Tabor's documentation says SMP but the physical connector is threaded with a protruding centre pin, so probably SMC or 1.0/2.3. Identify before ordering.
RESOLVED 2026-10-07 | 2x Marki MMD-1030LS - price | The whole interstage lineup branches on it: adopting it means ONE amp per chain instead of two, no 12.5 dB pad, no second ZX90, and an Rx output that lands on -6 dBm with no further parts. The November ZX60-83LN-S+ order shrinks from 4 to 2 (or 0). | RESOLVED - NO. $783.20 at qty 1-4, 0 in stock and 0 factory stock with no quotable lead time (Marki shop and RFMW agree). Two units would be $1,566.40 against $983.00 for the ZX90 route, whose parts are all on the shelf today. The ZX90 route is now primary.
RESOLVED 2026-10-07 | TB-830A+ interim boards: ships with SMA? lead time? | The user's requirement is SMA connectors. Standard for the MCL TB format but not shown on the product page. | MOOT - the question never has to be answered. ZX60-83LN-S+ is now MORE THAN 100 in stock at MCL direct, so buy the real connectorised part and drop the eval-board bridge entirely. Also removes the +5 V bench-supply wiring and the open-PCB handling.
NARROWED 2026-10-07 | November 2026 Mini-Circuits amp order | 3x ZX60-P105LN+ and 2-4x ZX60-83LN-S+ (plus ZX90-2-24-S+ #2 on the fallback route) were quoted at ~Nov 2026 and are the critical path. The interims retire to spares when they land. | NARROWED to ONE part. ZX60-83LN-S+ and ZX90-2-24-S+ are both in stock now. Only ZX60-P105LN+ remains: DigiKey says 0 in stock, 10 expected 04-Nov-2026, 30-week factory lead. Order the 3 units now to hold a queue position and buy from MCL at $119.47 rather than DigiKey at $143.36. Bridge the ~4 weeks with the owned H242 (Tx front, after the edge check), the owned 123LN (Rx front) and an ampless IF.
OPEN - ACST | Internal IF amp P1dB and overload recovery time | This is now the sole remaining determinant of dead time. The external IF chain is linear at typical power throughout, so settling is set by an amplifier inside a sealed box. | Ask. Unanswered as of 2026-08-05.
OPEN - ACST | MixAMC LO input absolute maximum - is -2 dBm an operating max or a damage limit? | Determines how much margin the Phase 1.7 trim needs. | Ask. Until answered, treat -2 dBm as a damage limit and never approach it.
OPEN - ACST | IF port low-frequency end, and whether any DC is present | Decides whether the BLK-18-S+ DC block is permanent. | Ask. The DC block stays in regardless until answered.
OPEN - ACST | Out-of-band input tolerance as a written dBc number | ACST said qualitatively on 2026-08-05 that out-of-band content does not matter to the AMC, and that is what dropped the FLP-1740 and the WR-62 section from the design. The interstage filters stay because they prevent IN-band products, not because of AMC protection. | Get it in writing. Leave a bolt-in gap for a back-to-back SMA-WR62 adapter pair (9.49 GHz cutoff) as a 10-minute A/B test if a 310-370 GHz artifact ever appears.
OPEN - bench | Does the doubler saturate? Tilt transfer ratio per stage | A square-law doubler doubles small-signal dB tilt; hard saturation drives the transfer toward zero. The design needs <=~1.2 per doubler to fit the AMC's 7 dB window. | Measure Pout vs Pin at step 2.6. The assumption currently rests on unmeasured parts.
OPEN - bench | AWG phase noise at 2.57 GHz | Worth one measurement at bring-up. Note that a 10 MHz external reference buys coherence and accuracy, not offset purity - a PLL disciplines only inside its ~100 Hz-kHz loop bandwidth. | One EXA measurement during Phase 0.